## Drawdown
Contingency Drawdown Tracker
Actual contingency remaining against the rate at which uncertainty is actually being resolved.
Fill the yellow cells only. Row 9 is a filled example.
Original contingency at approval | 8500000 | Enter once. All planned figures reference this cell.
Period | Percent complete | Contingency remaining | Planned remaining | Percent of contingency left | Variance vs plan | Status
EXAMPLE: Q1 FY26 | 30% | 3400000 | 5950000 | 40% | -2550000 | Consuming far faster than plan
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Planned remaining uses the simplest defensible baseline: contingency should be released roughly in proportion to work completed.
A programme that has consumed 60 percent of contingency at 30 percent completion has already told you the answer.
Replace the linear baseline with your own planned drawdown curve if you have one. The comparison is the point, not the shape.
This chart moves before the forecast does, because contingency is spent by the people doing the work while the forecast is defended in meetings.
Source for the practice: GAO-20-195G, Cost Estimating and Assessment Guide, contingency management.